## Sheet1
Master task list | Carl's Tasks (Product Owner) | Bryant's Tasks | Kenny's Tasks | Susie's Tasks | Zach's Tasks (Scrum Master: Sprint I)
Parser | WEEK ONE (10/5/15 - 10/9/15)
Syntax-tree object | Slide Presentation/Preparation | Slide Presentation | Slide Presentation | Slide Presentation | Slide Presentation
Bare-bones server | MathJax Presentation | Ruby Presentation | AngularJS Presentation | Ruby on Rails Presentation | JS Presentation
Bare-bones GUI | MathJax Cheatsheet | Ruby Cheatsheet | AngularJS Cheatsheet | Ruby on Rails Cheatsheet | JS Cheatsheet
Git Cheat Sheet | WEEK TWO (10/12/15 - 10/16/15)
User stories list/doc | Grammar | Site Structure (routes) | GUI | User story decomposition | User story decomposition
Brainstorm about manipulations | Parser | User story decomposition | User story decomposition | Hello Rails Server
Points system | User story decomposition
Make an alternative grammar for function definitions | WEEK THREE (10/19/15 - 10/23/15)
| Parser Integration (~1 hr) | Basic Route Integration with server (~1 hr) | LaTeX Tree Output (~3 hrs) | Ruby on Rails Authentication Presentation (~2-4 hrs) | JavaScript Classes (~4 hrs)
Glue together (~1 hr)
WEEK FOUR (10/26/15 - 10/30/15)
| Authentication: By the end of this week, the proiect should be using devise for authentication, and there should be a way to sign up, log in, logout, and a page that displays their username to verify that they are a logged in user. | Authentication: By the end of this week, the proiect should be using devise for authentication, and there should be a way to sign up, log in, logout, and a page that displays their username to verify that they are a logged in user. | GUI: By the end of this week, the main content box should be visible and partially completed, filled with the equiation view and a box for the tree view. There should also be boxes of equal height on the left and the right as placeholders for future toolboxes. | Navbar: By the end of this week, there should be a navigation bar at the top of the page that has the logo, a placeholder for the login button, and a dropdown menu with placeholders for other options. | Baby steps with Angular - Enter button: By the end of this week, pressing the enter key on the keyboard will do the same functionality as pressing the "Enter" button on the scratch pad with your mouse.
| Tree-view: By the end of this week, there should be a simple visualization for the math tree. |  |  |  | GUI: By the end of this week, the main content box should be visible and partially completed, filled with the equiation view and a box for the tree view. There should also be boxes of equal height on the left and the right as placeholders for future toolboxes.
Logistics: By Saturday evening, there should be a Logistics folder in the github account containing all of the logistic information about the project, including the Release Plan, the Sprint 1 Retrospective, the Sprint 1 plan and the Sprint 2 plan.