## Sheet1
Product Name: Algebreezy
Release ID: 1 |  | Sprint ID: 1
A) What worked well, and will be continued: • Group Cohesiveness • Visual whiteboard use • Long Weekend meetings • Everyone pulling own weight | C) New Implementations: • Live web-hosting • More Sprint II GUI development • Pair-programming • Test code for bugs before passing onto group • More specific user stories • Login/out page for website
B) What was problematic and will be changed: • User stories too general, implement "Unit Test"-like implementation/guidelines